## Decision log
Decision log
One row per decision: what was decided, why, who has to act, and where it was agreed.
Yellow cells with blue text are yours to fill in. Black text calculates. Rows marked as examples can be overwritten.
ID | Date | Decision | Why | Decided by | Who must act | Due by | Where | Source (message, email or call) | Status | Days open | Overdue
D-001 | 2026-10-12 | Move 022 Indigo kurta to 200 GSM fabric | 180 GSM failed QA's wash test | Founder | Mill, factory, buying | 2026-10-16 | WhatsApp | Founder in the 022 production group, 18:42 | Done
D-002 | 2026-10-14 | Add a second size check before dispatch for Mumbai orders | Two wrong-size shipments in September | Head of operations | Warehouse team | 2026-10-31 | Meeting | Weekly operations review | In progress
D-003 | 2026-10-20 | Pay vendor advances only against a PI that matches the PO | Two advances paid on old prices this quarter | Finance head | Accounts, merchandising | 2026-10-30 | Email | PI checks thread, 20 Oct | Agreed
Formulas:
Days open = IF(OR([Date]="",[Status]="Done",[Status]="Reversed"),"",TODAY()-[Date])
Overdue = IF(AND([Due by]<>"",[Due by]<TODAY(),[Status]<>"Done",[Status]<>"Reversed"),"Overdue","")
Note on C6: Example rows: overwrite or delete them.

## How to use
How to use the decision log
Five minutes to set up. Then keep it current as things change.
1 | Log a decision as soon as it's made, in the meeting, chat or call where it happened. Give it the next ID.
2 | Write why, in one line. It's the part everyone forgets, and the part you'll need when someone asks who approved it.
3 | Name who decided and who must act, and set a due date for the action.
4 | Record where it was agreed: pick the channel, and note the thread, email or call so anyone can find the source.
5 | Update the status as work moves. Days open and Overdue calculate themselves; review overdue rows weekly.
Use one log per team or project. Decisions that change something a partner relies on, like a price, a date or a version, are the ones most worth logging.
Made by Spurby. Spurby keeps sheets like this current from the WhatsApp, email and calls where things change: https://www.spurby.co