## T&A calendar
Time and action calendar
Planned dates work back from the ex-factory date. Enter a revised date when something moves, and the actual date when it's done.
Yellow cells with blue text are yours to fill in. Black text calculates. Rows marked as examples can be overwritten.
| Style number | 041 |  | Milestones late
| Style name | Linen overshirt |  | Due in the next 7 days
| Brand | Your brand |  | Done
| Factory | Your factory |  | Biggest move so far (days)
| Order quantity | 2400
| Ex-factory date | 2027-03-15
Today
# | Milestone | Owner | Days before ex-factory | Planned date | Revised date | Actual date | Status | Moved by (days) | Where it was agreed | Notes
1 | PO confirmed | Buying | 120 |  |  | 2026-11-15 |  |  | PO email from buying, 15 Nov (example)
2 | Tech pack issued to factory | Design | 115
3 | Lab dips submitted | Mill | 105
4 | Lab dips approved | Design | 98 |  | 2026-12-13 |  |  |  | WhatsApp, mill: second round of dips needed (example) | Shade C too green. Mill re-dipping.
5 | Fit sample submitted | Factory | 95
6 | Fit sample approved | Design, QA | 88
7 | Bulk fabric ordered | Sourcing | 85
8 | Trims approved | Merchandising | 80
9 | Strike-off approved (printed styles) | Design | 78
10 | PP sample submitted | Factory | 50
11 | PP sample approved | QA | 45
12 | Bulk fabric in-house | Mill, factory | 40
13 | Fabric tests passed | QA, lab | 35
14 | Cutting starts | Factory | 30
15 | Sewing starts | Factory | 25
16 | Inline inspection | QA | 15
17 | Finishing and packing | Factory | 7
18 | Final inspection (AQL) | QA | 3
19 | Ex-factory | Factory | 0
Lead times are examples. Change the days before ex-factory to match your product, mill and factory.
Note on C10: Replace with your ex-factory date. Every planned date counts back from it.
Note on F18: Example entry: the approval moved 6 days. Overwrite or clear it.

## How to use
How to use the time and action calendar
Five minutes to set up. Then keep it current as things change.
1 | Fill in the yellow cells at the top: style, factory, order quantity and the ex-factory date.
2 | Check the days before ex-factory for each milestone. They are examples; change them to your real lead times, and add or delete rows as you need.
3 | When a date moves, enter the revised date. The status and the moved-by column update themselves.
4 | When a milestone is done, enter the actual date. It turns blue.
5 | Write down where each change was agreed: the chat, email or call. When something slips later, you'll know who said what.
Status reads Late when the revised (or planned) date has passed without an actual date, and Due this week when it falls in the next 7 days. Review the sheet in your weekly production call.
Made by Spurby. Spurby keeps sheets like this current from the WhatsApp, email and calls where things change: https://www.spurby.co